## Order, Expected
|  | A | B | C | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | E | F | G | H
2 | 0
4 | 30
3 | 45 | 30
4 | 150 |  |  | 15
3 | 230 |  |  |  | 120
3 | 270 |  |  |  |  | 80
4 | 570 | [5 empty] | 120
3 | 630 | [6 empty] | 300
3 | 642 | [7 empty] | 60
3 | 862 | [8 empty] | 72
3 | 934 | [9 empty] | 220
2 | 966 | [10 empty] | 72
2 | 1600 | [13 empty] | 32
2 | 1652 |  | 1600
2 | 1704 | [11 empty] | 52
1 | 1736 | [12 empty] | 52
32

## Worst Case
taskID | task | Days Since Start | Duration | Days Since Completion | taskID | task | Start Timeline | End Timeline | Duration
A | Describe product | 0 | 40 | 40 | A | Describe product | 0 | 40 | 40
B | Develop marketing strategy | 0 | 2400 | 2400 | B | Develop marketing strategy | 0 | 2400 | 2400
C | Design brochure | 40 | 20 | 60 | C | Design brochure | 40 | 60 | 20
D1 | Requirements analysis | 40 | 160 | 200 | D1 | Requirements analysis | 40 | 200 | 160
D2 | Software design | 200 | 120 | 320 | D2 | Software design | 200 | 320 | 120
D3 | System design | 200 | 160 | 360 | D3 | System design | 200 | 360 | 160
D4 | Coding | 360 | 480 | 840 | D4 | Coding | 360 | 840 | 480
D5 | Write documentation | 840 | 80 | 920 | D5 | Write documentation | 840 | 920 | 80
D6 | Unit testing | 840 | 120 | 960 | D6 | Unit testing | 840 | 960 | 120
D7 | System testing | 960 | 320 | 1280 | D7 | System testing | 960 | 1280 | 320
D8 | Package deliverables | 1280 | 120 | 1400 | D8 | Package deliverables | 1280 | 1400 | 120
G | Develop implementation plan | 1400 | 40 | 1440 | G | Develop implementation plan | 1400 | 1440 | 40
E | Survey potential market | 2400 | 80 | 2480 | E | Survey potential market | 2400 | 2480 | 80
F | Develop pricing plan | 2480 | 80 | 2560 | F | Develop pricing plan | 2480 | 2560 | 80
H | Write client proposal | 2560 | 40 | 2600 | H | Write client proposal | 2560 | 2600 | 40

## Expected, Sensitivity
taskID | task | Days Since Start | Duration | Original Duration | New Duration | End | taskID | task | Start Timeline | End Timeline | Duration
A | Describe product | 0 | 30 | 30 |  | 30 | A | Describe product | 0 | 30 | 30
B | Develop marketing strategy | 0 | 320 | 1600 | 320 | 320 | B | Develop marketing strategy | 0 | 320 | 320
C | Design brochure | 30 | 15 | 15 |  | 45 | C | Design brochure | 30 | 45 | 15
D1 | Requirements analysis | 30 | 120 | 120 |  | 150 | D1 | Requirements analysis | 30 | 150 | 120
D2 | Software design | 150 | 80 | 80 |  | 230 | D2 | Software design | 150 | 230 | 80
D3 | System design | 150 | 120 | 120 |  | 270 | D3 | System design | 150 | 270 | 120
D4 | Coding | 270 | 300 | 300 |  | 570 | D4 | Coding | 270 | 570 | 300
D5 | Write documentation | 570 | 60 | 60 |  | 630 | D5 | Write documentation | 570 | 630 | 60
D6 | Unit testing | 570 | 72 | 72 |  | 642 | D6 | Unit testing | 570 | 642 | 72
D7 | System testing | 642 | 220 | 220 |  | 862 | D7 | System testing | 642 | 862 | 220
D8 | Package deliverables | 862 | 72 | 72 |  | 934 | D8 | Package deliverables | 862 | 934 | 72
G | Develop implementation plan | 934 | 32 | 32 |  | 966 | G | Develop implementation plan | 934 | 966 | 32
E | Survey potential market | 320 | 10.4 | 52 | 10.4 | 330.4 | E | Survey potential market | 320 | 330.4 | 10.4
F | Develop pricing plan | 934 | 10.4 | 52 | 10.4 | 944.4 | F | Develop pricing plan | 934 | 944.4 | 10.4
H | Write client proposal | 944.4 | 6.4 | 32 | 6.4 | 950.8 | H | Write client proposal | 944.4 | 950.8 | 6.4
E | Survey potential market | B, C
F | Develop pricing plan | D8, E
G | Develop implementation plan | A, D8

## Expected
taskID | task | Days Since Start | Duration | Days Since Completion | taskID | task | Start Timeline | End Timeline | Duration
A | Describe product | 0 | 30 | 30 | A | Describe product | 0 | 30 | 30
B | Develop marketing strategy | 0 | 1600 | 1600 | B | Develop marketing strategy | 0 | 1600 | 1600
C | Design brochure | 30 | 15 | 45 | C | Design brochure | 30 | 45 | 15
D1 | Requirements analysis | 30 | 120 | 150 | D1 | Requirements analysis | 30 | 150 | 120
D2 | Software design | 150 | 80 | 230 | D2 | Software design | 150 | 230 | 80
D3 | System design | 150 | 120 | 270 | D3 | System design | 150 | 270 | 120
D4 | Coding | 270 | 300 | 570 | D4 | Coding | 270 | 570 | 300
D5 | Write documentation | 570 | 60 | 630 | D5 | Write documentation | 570 | 630 | 60
D6 | Unit testing | 570 | 72 | 642 | D6 | Unit testing | 570 | 642 | 72
D7 | System testing | 642 | 220 | 862 | D7 | System testing | 642 | 862 | 220
D8 | Package deliverables | 862 | 72 | 934 | D8 | Package deliverables | 862 | 934 | 72
G | Develop implementation plan | 934 | 32 | 966 | G | Develop implementation plan | 934 | 966 | 32
E | Survey potential market | 1600 | 52 | 1652 | E | Survey potential market | 1600 | 1652 | 52
F | Develop pricing plan | 1652 | 52 | 1704 | F | Develop pricing plan | 1652 | 1704 | 52
H | Write client proposal | 1704 | 32 | 1736 | H | Write client proposal | 1704 | 1736 | 32

## Best Case
taskID | task | Days Since Start | Duration | Days Since Completion | taskID | task | Start Timeline | End Timeline | Duration
A | Describe product | 0 | 20 | 20 | A | Describe product | 0 | 20 | 20
B | Develop marketing strategy | 0 | 800 | 800 | B | Develop marketing strategy | 0 | 800 | 800
C | Design brochure | 20 | 10 | 30 | C | Design brochure | 20 | 30 | 10
D1 | Requirements analysis | 20 | 80 | 100 | D1 | Requirements analysis | 20 | 100 | 80
D2 | Software design | 100 | 40 | 140 | D2 | Software design | 100 | 140 | 40
D3 | System design | 100 | 80 | 180 | D3 | System design | 100 | 180 | 80
D4 | Coding | 180 | 120 | 300 | D4 | Coding | 180 | 300 | 120
D5 | Write documentation | 300 | 40 | 340 | D5 | Write documentation | 300 | 340 | 40
D6 | Unit testing | 300 | 24 | 324 | D6 | Unit testing | 300 | 324 | 24
D7 | System testing | 324 | 120 | 444 | D7 | System testing | 324 | 444 | 120
D8 | Package deliverables | 444 | 24 | 468 | D8 | Package deliverables | 444 | 468 | 24
G | Develop implementation plan | 468 | 24 | 492 | G | Develop implementation plan | 468 | 492 | 24
E | Survey potential market | 800 | 24 | 824 | E | Survey potential market | 800 | 824 | 24
F | Develop pricing plan | 824 | 24 | 848 | F | Develop pricing plan | 824 | 848 | 24
H | Write client proposal | 848 | 24 | 872 | H | Write client proposal | 848 | 872 | 24